## TEAM 1
North Rural Unsealed Road Maintenance Grading Program to December 2024 - Subject to Change and weather dependant
Crew: | TEAM 1
(July 2024 & October 2024 )
(August 2024 & November 2024)
(September 2024 & December 2024)
Road ID | Road | Suburb
WEEK 1 | JULY 2024
| OLD KAIPARA RD | KAIPARA FLATS
| CLEMENTS HILL LANE | KAIPARA FLATS
| THOMSON RD (KAIPARA FLATS) | KAIPARA FLATS
| GUY RD | KAIPARA FLATS
| DAVIE MARTIN RD | KAIPARA FLATS
| KAPONGA LANE | KAIPARA FLATS
| KAIPARA HILLS RD | KAIPARA FLATS
| DILL RD | KAIPARA FLATS
| BROTT RD | KAIPARA FLATS
WEEK 2 | JULY 2024
| MAINLAND RD | KAIPARA FLATS
| HAWKING RD | KAIPARA FLATS
| FLETCHER LANE | KAIPARA FLATS
| EVES RD | KAIPARA FLATS
| KAIPARA HILLS RD | KAIPARA FLATS
WEEK 3 | JULY 2024
| KAIPARA HILLS RD | KAIPARA FLATS
| OGLE RD | MANGAKURA
| TAUHOA RD | MANGAKURA
| DYER RD | WELLSFORD
| POYNTER RD | MANGAKURA
WEEK 4 | JULY 2024
| J MASON RD | MANGAKURA
| TAUHOA RD | MANGAKURA
| HOTEO STATION RD | DOME FOREST
| HOTEO RIVER RD | MANGAKURA
| HUDSON LANE | KAIPARA FLATS
| KAITOTO RD | KAIPARA FLATS
| STREAMLANDS SWAMP RD | KAIPARA FLATS
| IRVINE RD | DOME FOREST
| LINTON RD | KAIPARA FLATS
| MATTHEW RD | KAIPARA FLATS
| BARR RD (KAKANUI) | MAKARAU
WEEK 1 | AUGUST 2024
| TUHIRANGI RD | MAKARAU
| MAKARAU RD | MAKARAU
| BURKE RD | MAKARAU
| EAGLE VIEW RISE | MAKARAU
| BURNSIDE RD (MAKARAU) | MAKARAU
| RAUHORI RD | MAKARAU
| CAMERON WAY | MAKARAU
WEEK 2 | AUGUST 2024
| WECH ACCESS | MAKARAU
| MARTIN ACCESS RD | MAKARAU
| WILSON RD (KOMOKORIKI) | MAKARAU
| KOMOKORIKI HILL RD | MAKARAU
| POYNER RD | MAKARAU
WEEK 3 | AUGUST 2024
| PARKER RD (KOMOKORIKI) | MAKARAU
| HAWKENS RD | MAKARAU
| AHUROA RD | PUHOI
| CLIFFORD RD (AHUROA) | MAKARAU
| AHUROA VALLEY RD | MAKARAU
| J TOLHOPF RD | PUHOI
WEEK 4 | AUGUST 2024
| REMIGER RD | PUHOI
| TUNNEL RD | PUHOI
| LENZEN RD | PUHOI
| J TURNWALD RD | PUHOI
| SALEYARDS RD (PUHOI) | PUHOI
| KRIPPNER RD | PUHOI
| WENZ BAYER RD | PUHOI
| GRANT RIDGE RD | PUHOI
| SIMON BAYER RD | PUHOI
WEEK 5 | AUGUST 2024
| NOAKES HILL RD | PUHOI
| GREEN HOLLOWS RD | PUHOI
| FOWLER ACCESS RD | PUHOI
| BILLING RD | PUHOI
| BILLING RD EXT | PUHOI
| HUNGRY CREEK RD | PUHOI
| PUKAPUKA RD | POHUEHUE
| NGAREWA DR | MAHURANGI WEST
| MOIR HILL RD | WARKWORTH
WEEK 1 | SEPTEMBER 2024
| COWAN BAY RD | WARKWORTH
| PERRY RD | WARKWORTH
| SATELLITE STATION RD | WARKWORTH
| WYLLIE RD (WARKWORTH) | WARKWORTH
| THOMPSON RD (NORTH) | WARKWORTH
| WILSON RD (WARKWORTH) | WARKWORTH
WEEK 2 | SEPTEMBER 2024
| HODGART RD | WARKWORTH
| EDWARDS RD (WARKWORTH) | WARKWORTH
| HAMILTON RD (WARKWORTH) | WARKWORTH
| DUCK CREEK RD (WARKWORTH) | WARKWORTH
| HAMILTON RD (WARKWORTH) | WARKWORTH
| LAWRIE RD | WARKWORTH
| GRANGE ST | WARKWORTH
| JAMES ST (SANDSPIT) | SNELLS BEACH
| DAWSON RD (SNELLS BEACH) | SNELLS BEACH
| RIDGE RD (MAHURANGI EAST) | MAHURANGI EAST
| SHORT ST (MAH EAST) | MAHURANGI EAST
| ROBERT ST (MAHURANGI EAST) | MAHURANGI EAST
| WILLIAMS ST (MAHURANGI EAST) | MAHURANGI EAST
| RIDGE RD (MAHURANGI EAST) LLA | MAHURANGI EAST
| LETT RD | SNELLS BEACH
| MILLER WAY | MAHURANGI EAST
| SCANDRETT RD | MAHURANGI EAST
| CROSS ST (SANDSPIT) | SNELLS BEACH
| BEACH ST | SANDSPIT
| WILLIAMS ST (SANDSPIT) | WARKWORTH
| WRIGHT RD (MATAKANA) | MATAKANA
WEEK 3 | SEPTEMBER 2024
| QUIET RISE | MATAKANA
| WRIGHT RD (MATAKANA) | MATAKANA
| TONGUE FARM RD | MATAKANA
| WARD RD | MATAKANA
| SMITH RD | MATAKANA
| ANDERSON RD (MATAKANA) | MATAKANA
| GOLF RD (WARKWORTH) | WARKWORTH
| CLAYDEN RD | WARKWORTH
| SANDERSON RD | WARKWORTH
| CONICAL PEAK RD | DOME VALLEY
WEEK 4 | SEPTEMBER 2024
| WAIWHIU RD | DOME VALLEY
| KRAACK RD | DOME FOREST
| PHILLIPS RD (DOME FOREST) | DOME FOREST
| MARUA WAY | DOME FOREST
| SMYTH RD | DOME FOREST
| EDGERLEY RD | KAIPARA FLATS

## TEAM 2
North Rural Unsealed Road Maintenance Grading Program to December 2024 - Subject to Change and weather dependant
Crew : | TEAM 2
(July 2024 & October 2024 )
(August 2024 & November 2024)
Road ID | Road | Suburb
WEEK 1 | JULY 2024
| OKAHUKURA RD | TAPORA
| FITZGERALD RD (TAPORA) | TAPORA
| RUN RD | TAPORA
WEEK 2 | JULY 2024
| KAKARAEA RD | TAPORA
| LEMON TREE BAY RD | TAPORA
| BURMA RD | TAPORA
WEEK 3 | JULY 2024
| MARSH RD | WHAREHINE
| PAH HILL RD | WHAREHINE
| SHEGADEEN RD | WHAREHINE
| BEAVER RD | WHAREHINE
| GRICE RD | WHAREHINE
| WITHEFORD RD | WHAREHINE
WEEK 4 | JULY 2024
| WHAREHINE RD | WHAREHINE
| CORLETT RD | TAUHOA
| FORDYCE RD (TAUHOA) | TAUHOA
| BOLER RD | TAUHOA
| NAUMAI RD | TAUHOA
| LITTIN RD (TAUHOA) | TAUHOA
| J FARMER RD | TAUHOA
| OMAUMAU RD | GLORIT
| JV GRANT RD | PORT ALBERT
| HEAVEN RD | WHAREHINE
| PETTET RD | WELLSFORD
| JV GRANT RD | PORT ALBERT
| UNDERWOOD RD | PORT ALBERT
| GUM TREE LANE | WELLSFORD
WEEK 1 | AUGUST 2024
| UNDERWOOD RD | PORT ALBERT
| PARTRIDGE RD | WELLSFORD
| BIDDLE RD | WELLSFORD
| MCCAHON RD | WELLSFORD
| BOOTH RD | WELLSFORD
| BENNETT ST (PORT ALBERT) | PORT ALBERT
| WHARF RD (PORT ALBERT) | PORT ALBERT
| CHURCH HILL RD | PORT ALBERT
| BM GUBBS RD | PORT ALBERT
WEEK 2 | AUGUST 2024
| HARATAUA RD | PORT ALBERT
| BAY RD (PORT ALBERT) | PORT ALBERT
| BECROFT RD | WELLSFORD
| TAMERLANE RD | WELLSFORD
| WILLIAMSON RD | WELLSFORD
| WORKER RD (NORTH END) | WELLSFORD
| MCGILLIVRAY RD | WELLSFORD
| HARDING RD | WELLSFORD
| INGLETON RD | WELLSFORD
| WAYBY STATION RD | WELLSFORD
| OLDFIELD RD (WAYBY) | WELLSFORD
WEEK 3 | AUGUST 2024
| OLDFIELD RD (WAYBY) | WELLSFORD
| WAYBY STATION RD | WELLSFORD
| GRUMPY RD | WELLSFORD
| COX RD | WELLSFORD
| MCPHERSON WAY | WELLSFORD
| SPINDLER RD | WELLSFORD
| ROBERTSON RD (WAYBY) | WELLSFORD
| RUSTYBROOK RD | WELLSFORD
| FLAGSTAFFE RD | WELLSFORD
| WILSON RD (WAYBY VALLEY) | WELLSFORD
| HOMEWARD BOUND DR | WELLSFORD
| MILLETT RD | WHANGARIPO
| PETRIE RD | WHANGARIPO
| KENNAWAY RD | WHANGARIPO
| GOVAN WILSON RD | WHANGARIPO

## TEAM 3
North Rural Unsealed Road Maintenance Grading Program to December 2024 - Subject to Change and weather dependant
Crew: | TEAM 3
(July 2024 & October 2024 )
(August 2024 & November 2024)
(September 2024 & December 2024)
(October 2024 (End)
Road ID | Road | Suburb
WEEK 1 | JULY 2024
| HARURU RD | KAUKAPAKAPA
| ADAMS RD (WAINUI) | KAUKAPAKAPA
| KANOHI RD | KAUKAPAKAPA
| GATFIELD RD | KAUKAPAKAPA
| CORY RD (KANOHI) | KAUKAPAKAPA
| O'NEIL RD | KAUKAPAKAPA
WEEK 2 | JULY 2024
| HELLYER RD | KAUKAPAKAPA
| RIX RD | KAUKAPAKAPA
| ROKU RISE | KAUKAPAKAPA
| TIRO WAINUI RD | TAHEKEROA
| TAHEKEROA RD | TAHEKEROA
| MICK DILLON RD | TAHEKEROA
| BLARK RD | TAHEKEROA
| JOWSEY ACCESS RD | TAHEKEROA
| RAUNER RD | TAHEKEROA
| UPPER WAIWERA RD | PUHOI
| WOOD ACCESS RD | PUHOI
WEEK 3 | JULY 2024
| UPPER WAIWERA RD | PUHOI
| BAYER RD | PUHOI
| BROADY RD | PUHOI
| WERANUI RD (RURAL) | WAINUI
| MCCATHIE RD | PUHOI
| RUSSELL RD (WAINUI) | WAINUI
| KOWHAI RD (WAINUI) | OREWA
| LYSNAR RD (WAINUI) | WAINUI
| CEMETERY RD (WAINUI) | WAINUI
| GERVIN RD | WAINUI
WEEK 4 | JULY 2024
| JOBLIN RD | WAINUI
| PEBBLE BROOK RD | WAITOKI
| SHARON RD (WAITOKI) | WAITOKI
| QUARRY RD (WAITOKI) | WAITOKI
| FROST RD (DAIRY FLAT) | WAITOKI
| ATTITUDE AVE | WAITOKI
| YOUNG ACCESS | DAIRY FLAT
| OLD PINE VALLEY RD | DAIRY FLAT
| AUSTIN RD (DAIRY FLAT) | DAIRY FLAT
| BLAKE LANE | DAIRY FLAT
| TENDER RD | DAIRY FLAT
| TURLEY RD | DAIRY FLAT
| SELMAN RD | DAIRY FLAT
WEEK 1 | AUGUST 2024
| WILKS RD WEST | DAIRY FLAT
| RICHARDS RD | DAIRY FLAT
| FOLEY QUARRY RD | DAIRY FLAT
| DRURY LANE | DAIRY FLAT
| BLACKB RD (DAIRY FLAT) | DAIRY FLAT
| BALD HILL RD (RIVERHEAD) | WAITOKI
| IRELAND RD (WAITOKI) | WAITOKI
WEEK 2 | AUGUST 2024
| JACK BARRY RD | WAITOKI
| BURNE RD | WAITOKI
| WINDMILL GLEN RD | DAIRY FLAT
| BALD HILL RD (RIVERHEAD) | WAITOKI
| VALLEY RD (WAITOKI) | WAITOKI
| ARARIMU VALLEY RD | HELENSVILLE
| FORESTRY RD (RIVERHEAD) | RIVERHEAD
| LATHROPE RD | KUMEU
WEEK 3 | AUGUST 2024
| BEACON RD | RIVERHEAD
| TROTTING COURSE DR | KUMEU
| WORRALL RD | KUMEU
| FORK RD | KUMEU
| KAURI CRES (WAIMAUKU) EAST | WAIMAUKU
| KAURI CRES (WAIMAUKU) WEST | WAIMAUKU
| MATATEA RD | WAIMAUKU
| CABLE RD | WAIMAUKU
| VALLEY RD (WAIMUKU) | WAIMAUKU
| TAIAPA RD | MURIWAI
| CONSTABLE RD (MURIWAI) | MURIWAI
| COSTER RD | MURIWAI
| DOMAIN CRES LLA (#66 - #90) | MURIWAI
| HAMILTON RD (WAIMAUKU) | WAIMAUKU
WEEK 4 | AUGUST 2024
| FLETCHER RD | WAIMAUKU
| MAHANA RD | WAIMAUKU
| WINTOUR RD | WAIMAUKU
| MCPIKE RD (WOODHILL) | WAIMAUKU
| KIWITAHI RD | HELENSVILLE
| ALF ACCESS RD | HELENSVILLE
| DAVIDSON RD | HELENSVILLE
| KAIPARA VIEW RD | HELENSVILLE
| TARRANT RD | HELENSVILLE
| WHAREPAPA RD | HELENSVILLE
| HUTCHINSON RD | HELENSVILLE
WEEK 5 | AUGUST 2024
| BRADLY RD | HELENSVILLE
| TE PUA SCHOOL RD | HELENSVILLE
| TE PUA SCHOOL RD ACCESS RD | HELENSVILLE
| FORDYCE RD (PARAKAI) | HELENSVILLE
| GREEN RD (PARAKAI) | PARAKAI
| EVANS RD (PARKHURST) | SOUTH HEAD
| TARAWERA RD | SOUTH HEAD
| HARANUI RD | SOUTH HEAD
WEEK 1 | SEPTEMBER 2024
| SLATER RD | SOUTH HEAD
| WILSON RD (SOUTH HEAD) | SOUTH HEAD
| TE KANAE RD | SOUTH HEAD
| SHINE RD | SOUTH HEAD
| WEBBER RD | SOUTH HEAD
| MAIRETAHI RD | SOUTH HEAD
| MCMURDO RD | SOUTH HEAD
WEEK 2 | SEPTEMBER 2024
| MCLEOD RD (WAIONEKE) | SOUTH HEAD
| MONK RD | SOUTH HEAD
| HIGHAM RD | SOUTH HEAD
| FULLER RD | SOUTH HEAD
| DONOHUE RD | SOUTH HEAD
| TRIG RD (SOUTH HEAD KAIPARA) | SOUTH HEAD
| SOUTH HEAD RD | SOUTH HEAD
WEEK 3 | SEPTEMBER 2024
| MANGAKURA RD | HELENSVILLE
| INLAND RD | HELENSVILLE
| SHEFFIELD RD | HELENSVILLE
| ABEL RD | KAUKAPAKAPA
| FERNGULLY RD | KAUKAPAKAPA
| ANDERSON RD (KAUKAPAKAPA) | KAUKAPAKAPA
WEEK 4 | SEPTEMBER 2024
| SHANKS RD | KAUKAPAKAPA
| CHATHAM RD (KAUKAPAKAPA) | KAUKAPAKAPA
| DORMER RD | KAUKAPAKAPA
| SINCLAIR RD (KAUKAPAKAPA) | KAUKAPAKAPA
| MACKY RD | KAUKAPAKAPA
| HENLEY RD (KAUKAPAKAPA) | KAUKAPAKAPA
| BASIL ORR RD | KAUKAPAKAPA
| JORDAN RD (MAKARAU) | KAUKAPAKAPA
| NGAPUKE RD | KAUKAPAKAPA
| QUAIL RD | KAUKAPAKAPA
WEEK 1 | OCTOBER 2024
| MCLACHLAN RD | KAUKAPAKAPA
| ALPINE RD (KAUKAPAKAPA) NORTH | KAUKAPAKAPA
| HAFTON RD | KAUKAPAKAPA
| ONEWHERO RD | KAUKAPAKAPA
| PINCHGUT RD | KAUKAPAKAPA
| DOWNER ACCESS RD | KAUKAPAKAPA
| STONEY CREEK RD | KAUKAPAKAPA
| RAPSON RD (KAUKAPAKAPA) | KAUKAPAKAPA
| DYE ACCESS RD | KAUKAPAKAPA
| RAPSON ACCESS RD | WAITOKI

## TEAM 4
North Rural Unsealed Road Maintenance Grading Program to December 2024 - Subject to Change and weather dependant
Crew: | TEAM 4
(July 2024 & October 2024 )
(August 2024 & November 2024)
(September 2024 & December 2024)
Road ID | Road | Area
WEEK 1 | JULY 2024
| PAKIRI RIVER RD | PAKIRI
| WITTEN RD | PAKIRI
| SPENCER RD (PAKIRI ) | PAKIRI
| M GREENWOOD RD | LEIGH
| J GREENWOOD RD | LEIGH
| RODNEY RD (PAKIRI) | WHANGATEAU
| CAPE RODNEY RD | LEIGH
| MATHESON BUSH RD | LEIGH
| MOUNT PLEASANT DR | LEIGH
| OLD SCHOOL RD | LEIGH
| TENETAHI RD | LEIGH
| FROST RD (MATHESON BAY) | LEIGH
| KOURATAKI RD | LEIGH
| KOWHAI TCE NORTH | LEIGH
WEEK 2 | JULY 2024
| TAIRERE RD | TI POINT
| COXHEAD CREEK RD | WHANGATEAU
| ASHTON RD (OMAHA) | WHANGATEAU
| BIRDSALL RD | WHANGATEAU
| OMAHA WHARF RD | WHANGATEAU
| UPPER WHANGATEAU RD | BIG OMAHA
| SCHOLLUM RD | BIG OMAHA
| QUINTAL RD | BIG OMAHA
| HAYWOOD LANE | TAWHARANUI PENINSULA
| BISHOP LANE | TAWHARANUI PENINSULA
| TONGUE FARM RD | Matakana
| ROSS RD | TOPUNI
| MAENEENE RD | WELLSFORD
| WAIMANU RD | WELLSFORD
WEEK 3 | JULY 2024
| VIPOND RD (TOPUNI) | WELLSFORD
| RANGIWHAPAPA LANE | TE HANA
| CORONATION ST (TE HANA) | TE HANA
| AWAPEKA RD | TE HANA
| SILVER HILL RD | WELLSFORD
| SHEPHERD RD | WELLSFORD
| HINDLE RD | WELLSFORD
| BAILEY RD (TE HANA) | WELLSFORD
| LOWER SILVERHILL RD | WELLSFORD
| PARKER RD (TE HANA) | WELLSFORD
| WHARFE RD | WELLSFORD
WEEK 4 | JULY 2024
| VIPOND RD (MANGAWHAI) | WELLSFORD
| BOSHER RD | WELLSFORD
| REID UNDERPASS | WELLSFORD
| WORTHINGTON RD | WELLSFORD
| FARMERS LIME RD | WELLSFORD
| BORROW RD | WELLSFORD
| DAY RD (WAITEITEI) | WELLSFORD
| BOYD ACCESS RD | WHANGARIPO
| TAPU BUSH RD | WHANGARIPO
WEEK 1 | AUGUST 2024
| FISHLOCK RD | TE ARAI
| POOL RD | TE ARAI
| GORDON WAY | TE ARAI
| POOL RD | TE ARAI
| RYAN RD (TOMARATA) | TE ARAI
| PAMPAS LANE | TE ARAI
WEEK 2 | AUGUST 2024
| BRADDICK RD | TE ARAI
| KEITH RD | TE ARAI
| STANIFORTH RD | TE ARAI
| CAMES RD (TE ARAI) | MANGAWHAI
| BLACK SWAMP RD | MANGAWHAI
| COAL HILL RD | MANGAWHAI
| TE ARAI POINT RD | TE ARAI
WEEK 3 | AUGUST 2024
| TE ARAI POINT RD | TE ARAI
| OCEAN VIEW RD (TE ARAI) | TE ARAI
| LAKE RD (TE ARAI) | TE ARAI
| RED HILL RD (TE ARAI) | TE ARAI
| CEMETERY RD (TE ARAI) SOUTH | TE ARAI
WEEK 4 | AUGUST 2024
| BUSBRIDGE RD | TE ARAI
| OCEAN VIEW RD (TE ARAI) | TE ARAI
| ATKINS RD | TE ARAI
| GRANVILLE RD | TE ARAI
| CIVIL RD | TE ARAI
| CREST RD | TE ARAI
| PAKIRI BLOCK RD | TOMARATA
WEEK 5 | AUGUST 2024
| PAKIRI BLOCK RD | TOMARATA
| MEIKLE RD | TOMARATA
| RAHUIKIRI RD | TOMARATA
WEEK 1 | SEPTEMBER 2024
| DUNNING RD | TOMARATA
| SCHOOL RD (TOMARATA) | TOMARATA
| RADCLIFFE RD | TOMARATA
| PILLING RD | TOMARATA